## GOODS
PROCUREMENT OF GOODS
Procurement Entity: | SEKYERE EAST DISTRICT ASSEMBLY
Budget Period: | JAN-DEC 2022 | [5 empty] | Tender Documents
Source of Funding | DACF/IGF/DDF/SIF/GETFUND |  | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Goods Delivery
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
Duration
1. Procurement of Office Facilities, Supplies and Accessories. | Plan | AR/SEDA/GDS/01/22 | 126,000 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/2/2022 | 03/02/2022 | 05/02/2022 | Plan | 126,000 | 2022-12-02 | 18/02/2022 | 4/3/2022 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
2. Procurement and Installation of 100no 9m low Tension. | Plan | AR/SEDA/GDS/02/22 | 55350 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 55350 | 2022-12-02 | 18/3/2022 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
3. Purchase of Office Equipment.. | Plan | AR/SEDA/GDS/03/22 | 14300 | PQ | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 14300 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
4. Procurement of Cleaning Materials. | Plan | AR/SEDA/GD/04/21 | 21000 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 21000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
5. Procurement of Building Materials for Community Initiative Projects. | Plan | AR/SEDA/GDS/05/22 | 228568 | NTC | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 228568 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
6. Procurement of Relief items for Disaster Victims in the District. | Plan | AR/SEDA/GDS/06/22 | 15000 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 15000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
7. Procurement of Office Materials and Consumables. | Plan | AR/SEDA/GDS/07/22 | 5000 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 5000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
8. Purchasing of items for the Furnishing of DCE Bungalow. | Plan | AR/SEDA/GDS/08/22 | 90000 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 90000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
9. Procurement of Printed Materials and Stationery. | Plan | AR/SEDA/GD/09/22 | 92500 | NTC | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 92500 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-02
| Actual |  |  |  |  | Actual | [5 empty] | Actual
10. Procurement of Contruction Materials for self Help Project. | Plan | AR/SEDA/GDS/10/22 | 50000 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 50000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-02
| Actual |  |  |  |  | Actual | [5 empty] | Actual
11. Procurement of Toiletries items. | Plan | AR/SEDA/GDS/11/22 | 70184 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 70184 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
12. Procurement of Sawing Machines. | Plan | AR/SEDA/GDS/12/22 | 70000 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 70000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Plan
13 Procurement of Office Furniture. | Plan | AR/SEDA/GDS/13/22 | 80000 | NTC | ETC | Plan | 2022-08-01 | 15/2/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 80000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
14. Procurement of Value Books. | Plan | AR/SEDA/GDS/14/22 | 10000 | PQ | EH | Plan | 2022-08-01 | 15/2/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 10000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
15. Procurement and Installation of 200 No. 9m low Tension. | Plan | AR/SEDA/GDS/15/22 | 180000 | NCT | ETC | Plan | 2022-08-01 | 15/2/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 180000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
16. Procurement of 200 Complete Fixing. | Plan | AR/SEDA/GDS/16/22 | 100000 | NCT | ETC | Plan | 2022-08-03 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 100000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
17. Procurement of Network and ICT Equipment. | Plan | AR/SEDA/GDS/17/22 | 10000 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 10000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
18. Procurement of Office Furniture for Selected Staff. | Plan | AR/SEDA/GDS/18/22 | 20000 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 20000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
19. Procurement of Plant and Machinery. | Plan | AR/SEDA/GDS/19/22 | 60000 | NCT | EH | Plan | 2022-08-01 | 5/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 60000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
20.Procurement of Trafic Light at Affiduase. | Plan | AR/SEDA/GDS/20/22 | 120000 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 120000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Plan
21. Procurement and Installation of Street of 100NO. Street Streetlights. | Plan | AR/SEDA/GDS/21/22 | 100000 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 100000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
E
22. Purchase of Relieve items for PLHIV Orphan. | Plan | AR/SEDA/GDS/22/22 | 2500 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 2500 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
23.Purchase of Airtime HIV. | Plan | AR/SEDA/GDS/23/22 | 200 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 200 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
24. Procurment items for the Cerebration of Farmers Day. | Plan | AR/SEDA/GDS/24/22 | 71000 | NCT | ETC | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 71000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
25. Purchase of Computers &Accessories. | Plan | AR/SEDA/GD/25/22 | 25180 | PQ | EH | Plan | 2022-08-01 | 5/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 25180 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
26. Procurement of Refreshment of items. | Plan | AR/SEDA/GDS/26/22 | 8000 | PQ | EH | Plan | 2022-08-01 | 5/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 8000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
27. Purchasing of Protective Clothing for Staff. | Plan | AR/SEDA/GD/27/22 | 4241 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 4241 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Plan
28 | Plan | AR/AASWDA/GD/28/22 | 10000 | PQ | EH | Plan | 2022-08-01 | 15/01/2022 | 29/1/2022 | 3/02/2022 | 5/02/2022 | Plan | 10000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
29 | Plan | AR/AASWDA/GD/15/21 | 1500 | PQ | EH | Plan | 2022-08-01 | 15/01/2022 | 29/1/2022 | 3/02/2022 | 5/02/2022 | Plan | 1500 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
30 | Plan | AR/AASWDA/GD/16/21 | 20000 | PQ | EH | Plan | 2022-08-01 | 15/01/2022 | 29/1/2022 | 3/02/2022 | 5/02/2022 | Plan | 20000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
31 | Plan | AR/SEDA/GDS/17/22 | 4241 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 4241 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
32 | Plan | AR/AASWDA/GD/18/22 | 1000 | PQ | EH | Plan | 2022-08-01 | 15/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 1000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual
33 | Plan | AR/AASWDA/GDS/19/20 | 1000 | PQ | EH | Plan | 2022-08-01 | 5/1/2022 | 29/1/2022 | 3/2/2022 | 5/2/2022 | Plan | 1000 | 2022-12-02 | 2022-08-02 | 2022-04-03 | 2022-04-03
| Actual |  |  |  |  | Actual | [5 empty] | Actual

## WORKS
PROCUREMENT OF WORKS
Procurement Entity: | SEKYERE EAST DISTRICT ASSEMBLY
Budget Period: | JAN-DEC 2022 | [5 empty] | Tender Documents
Source of Funding | DACF/IGF/DDF/SIF/GETFUND |  | BASIC DATA |  |  |  |  | Tendering Period |  | Tender Evaluation |  |  | Contract Finalization |  |  | Contract Implementation
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Ex Agency | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Plan vs. Actual | Contract Amount (Cedis) | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Inspection Final Acceptance | Final cost
| Duration | [5 empty] | 2-4 wks | 2-4 wks |  | 2-4 wks | 1-2 wks |  |  | 1-2 wks | 1-3 wks | 2-4 wks | 6mths | 6 months
1. Renovation of Staff Residential. | Plan | AR/SEDA/WKS/01/22 | 160000 | NCT | ETC | Plan | 2022-08-01 | 13/01/22 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 160000 | 19/02/22 | 2022-05-03 | 19/03/22 | 18/06/22 | 26/11/2022 | 160000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
2.Renovation of DCE Residency | Plan | AR/SEDA/WKS/02/22 | 150000 | PQ | EH | Plan | 2022-08-01 | 13/01/22 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 150000 | 19/02/22 | 2022-05-03 | 19/03/22 | 18/06/22 | 26/11/2022 | 150000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
3. Completion of 1 N0. 3-Unit Classroom Block with Office,Store & 4 Seater Toilet at Naama. | Plan | AR/SEDA/WKS/03/22 | 40684 | PQ | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 40684 | 19/02/22 | 2022-05-03 | 19/3/2022 | 18/6/2022 | 26/11/2022 | 40684
| Actual |  |  |  |  | Actual | [5 empty] | Actual
4. Constructon of 2NO. 3-Unit Pavilion. | Plan | AR/SEDA/WKS/04/22 | 140000 | NCT | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 140000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/6/2022 | 26/11/2022 | 140000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
5. Completion of 2No. 3-Unit Teachers Accommodation at Effiduase Presby Primary School. | Plan | AR/SEDA/WK/05/22 | 6000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 6000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/6/2022 | 26/11/2022 | 6000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
6. Completion of 1 No. KG Block @ Anunya. | Plan | AR/SEDA/WKS/06/22 | 26783 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 26783 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 26783
| Actual |  |  |  |  | Actual | [5 empty] | Actual
7. Completion of 1No. 3-Unit Classroom Block with Staff Accommodation Room,Office at Apemso. | Plan | AR/DA/SEDA/07/22 | 116701 | NCT | ETC | Plan | 2022-08-01 | 13/2/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 116701 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 116701
| Actual |  |  |  |  | Actual | [5 empty] | Actual
8. Completion of Nkwankwanua Health Centre | Plan | AR/SEDA/WKS/08/22 | 335065 | NCT | ETC | Plan | 2022-08-01 | 13/2/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 335065 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 335065
| Actual |  |  |  |  | Actual | [5 empty] | Actual
9. Maintenance of Office Buildings. | Plan | AR/SEDA/WKS/09/21 | 75000 | PQ | EH | Plan | 2022-08-01 | 13/2/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 75000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 75000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
10. Rehabilitation of 40 Lockable Stores at Asokore. | Plan | AR/SEDA/WKS/10/22 | 350000 | NCT | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 350000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 350000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
11. Completion of 1No CHPS Compound Motokrodua. | Plan | AR/SEDA/WKS/11/22 | 36806 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 36806 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 36806
| Actual |  |  |  |  | Actual | [5 empty] | Actual
12. Construction of 1No. 10 Seater Aqua Privy Toilet Facilities & Awaham Akokoase and Asokore. | Plan | AR/SEDA/WKS/12/22 | 120000 | NCT | ETC | Plan | 8/1/2022/ | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 120000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 120000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
13. . Construction of Effiduase Market Wall at Effiduase. | Plan | AR/SEDA/WKS/13/22 | 20000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 20000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 20000
[6 empty] | Actual | [5 empty] | Actual
14. Completion of Drilling and Mechanization of 3No Borehall at Asokore, Akua krom and Anyanfa. | Plan | AR/AASWDA/WKS/14/22 | 35034 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 35034 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 35034
| Actual |  |  |  |  | Actual | [5 empty] | Actual
15. Drilling & Mechanization of 3No. Borehole | Plan | AR/SEDA/WKS/15/22 | 13917 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 13917 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 13917
| Actual |  |  |  |  | Actual | [5 empty] | Actual
16. Construction of Police Station at Nyanfa/Okaikrom | Plan | AR/SEDA/WKS/16/22 | 120000 | NCT | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 120000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 120000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
17. Drilling and Mechanization of 3No. Boreholes at Effiduase | Plan | AR/SEDA/WKS/17/22 | 17619 | PQ | EH | Plan | 2022-08-01 | 13/2/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 17619 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 17619
| Actual |  |  |  |  | Actual | [5 empty] | Actual
18. Construction of 1no. 20-Unit Market Sheds at Senchi. | Plan | AR/SEDA/WKS/18/22 | 60500 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 60500 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 60500
| Actual |  |  |  |  | Actual | [5 empty] | Actual
19. Completion of Police Headquarters in Effiduase | Plan | AR/AASWDA/WKS/19/22 | 576000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 576000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 576
| Actual |  |  |  |  | Actual | [5 empty] | Actual
20. Reshaping of 15KM feeder Roads District Wide. | Plan | AR/SEDA/WKS/20/22 | 100000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 100000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 100000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
21. Drilling of 3No. Borehole @ SAADE and Tijania. | Plan | AR/AASWDA/WKS/21/22 | 90000 | NCT | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 90000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 90000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
22. Completion of of 1No. 20-Unit Market shed at Senchi & Okaikrom | Plan | AR/SEDA/WKS/22/22 | 12100 | NTC | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 12100 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 12100
| Actual |  |  |  |  | Actual | [5 empty] | Actual
23. Establishment of Industry under IDIF at Effiduase | Plan | AR/SEDA/WKS/23/22 | 10000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 10000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 10000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
24. Construction of 1No. 40-Unit Market Shed Brofoyedu. | Plan | AR/AASWDA/WKS/24/22 | 442419 | NTC | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 442419 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 442419
| Actual |  |  |  |  | Actual | [5 empty] | Actual
25.Maintenance of Market in the District. | Plan | AR/SEDA/WKS/25/22 | 5000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 5000 | 19/2/2022 | 2022-05-03 | 21/03/21 | 18/7/2022 | 26/11/2022 | 5000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
26. Construction of Steel Footbridge at Effuduase. | Plan | AR/SEDA/WKS/26/22 | 65000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 65000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 65000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
27. Construction of ICT Building Nkwankwanua. | Plan | AR/SEDA/WKS/27/22 | 145.735 | NTC | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 145735 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 145735
| Actual |  |  |  |  | Actual | [5 empty] | Actual
28. Completion of 1NO. 40-Unit Lockable Store at Asokore. | Plan | AR/SEDA/WKS/28/22 | 27909 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 27909 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 27909
| Actual |  |  |  |  | Actual | [5 empty] | Actual
29. Renovation of Bouya Primary Schools ( Bouya) | Plan | AR/SEDA/WKS/29/22 | 45000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 45000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 45000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
30. Completion of Steel Foot Bridge Asokore. | Plan | AR/SEDA/WKS/30/22 | 10000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 10000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 10000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
31. Construction of 2No. Borehole Effiduse/Asokore. | Plan | AR/SEDA/WKS/31/22 | 50000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 50000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 50000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
32. Completion of 1 No. KG Block at Nkwankwanua | Plan | AR/SEDA/WK/32/22 | 41849 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 41849 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 41849
| Actual |  |  |  |  | Actual | [5 empty] | Actual
33. Mechanization of 1No. Borehole Apemso. | Plan | AR/SEDA/WKS/33/22 | 20000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 20000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 20000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
34. Maintenance of Desilting Drains and Streams(Effiduase/Asokore) | Plan | AR/SEDA/WKS/34/21 | 200000 | NCT | ETC | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 200000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 200000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
36. Rehabilitation of Rain Storm Disaster Project at Effeduase. | Plan | AR/SEDA/WKS/28/22 | 34961 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 34961 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 34961
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan | AR/SEDA/WKS/29/22 | 20000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 20000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 20000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
| Plan | AR/SEDA/WKS/30/22 | 35000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 35000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 35000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
31. | Plan | AR/SEDA/WKS/31/22 | 20000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 20000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 20000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
32. | Plan | AR/SEDA/WK/32/22 | 35000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 35000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 35000
| Actual |  |  |  |  | Actual | [5 empty] | Actual
33. | Plan | AR/SEDA/WKS/33/22 | 20000 | PQ | EH | Plan | 2022-08-01 | 13/1/2022 | 27/1/2022 | 2022-10-02 | 17/2/2022 | Plan | 20000 | 19/2/2022 | 2022-05-03 | 19/3/2022 | 18/7/2022 | 26/11/2022 | 20000
| Actual |  |  |  |  | Actual | [5 empty] | Actual

## SERVICES
PROCUREMENT OF SERVICES
Procurement Entity: | SEKYERE EAST DISTRICT ASSEMBLY
Budget Peroid | JAN-DEC 2022
Source of Funding | DACF/IGF/DDF/SIF/GETFUND
Contract Package* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | Procurement Method | Final Authority for Contract Award | Plan vs. Actual | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
[7 empty] | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract ward | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Duration | [5 empty] | 1-2 wks | 4-12 wks | 2-3 wks |  | 2 wks | 1-2 wks | 1-2 wks | Duration | 2 wks | 1-2 wks | 1-2 wks |  | 1 wk |  |  | 1-3 wks
1. Capacity Building Training for Staff. | Plan | AR/SEDA/CS/01/22 | 58859 | NTC | ETC | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2021-02-03 | 2022-04-03 | 58859 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/252 | 58859
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
2. Maintenance of Office Equipment. | Plan | AR/SEDA/CS/02/22 | 36237 | PQ | EH | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 36237 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/21 | 36.237
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
3. Maintance of Furniture and Fixtures. | Plan | AR/SEDA/TS/03/22 | 2000 | PQ | EH | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 2000 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2021 | 26/3/2022 | 31/03/22 | 2000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Plan
4. Maintenance and repair of Official Vehicle. | Plan | AR/SEDA/TS/04/22 | 64000 | NCT | ETC | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 64000 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/21 | 64000
| Actual |  |  |  |  | Actual | [7 empty] | Actual
5. Maintenance of Computer Soft Ware. | Plan | AR/SEDA/TS/05/22 | 20000 | PQ | EH | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 20000 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/21 | 20000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
6.Fumigation and Santation Management. | Plan | AR/AASWDA/TS/06/22 | 110000 | NTC | ETC | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 110000 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/22 | 110000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
7. Repair of Office Equipment. | Plan | AR/SEDA/TS/07/22 | 32137 | PQ | EH | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 32137 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/22 | 32137
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
8 | Plan | AR/SEDA/TS/08/22 | 36237 | PQ | EH | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 36.237 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/22 | 36237
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
9 | Plan | AR/SEDA/TS/09/22 | 20000 | PQ | EH | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2022-01-03 | 2022-02-03 | 2022-04-03 | 20000 | 2022-05-03 | 2022-10-03 | Plan | 24/03/2022 | 26/3/2022 | 31/03/22 | 20
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
10 | Plan | AR/SEDA/TS/07/22 | 110000 | NCT | ETC | Plan | 18/1/2022 | 25/01/22 | 2022-08-02 | 15/02/2022 | 22/02/22 | 14/2/2022 | 26/02/22 | Plan | 2021-01-03 | 2021-02-03 | 2021-04-03 | 110000 | 2021-05-03 | 2021-10-03 | Plan | 24/03/2021 | 26/3/2021 | 31/03/21 | 110000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
11 | Plan | AR/SEDA/TS/08/22 | 20000 | PQ | EH | Plan | 18/1/2021 | 25/01/21 | 2021-08-02 | 15/02/2021 | 22/02/21 | 14/2/2021 | 26/02/21 | Plan | 2021-01-03 | 2021-02-03 | 403/21 | 20000 | 2021-05-03 | 2021-10-03 | Plan | 24/03/2021 | 26/3/2021 | 31/03/21 | 20
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual
9 | Plan | AR/AASWDA/TS/09/21 | 212000 | PQ | EH | Plan | 18/1/2021 | 25/01/21 | 2021-08-02 | 15/02/2021 | 22/02/21 | 14/2/2021 | 26/02/21 | Plan | 2021-01-03 | 2021-02-03 | 2021-04-03 | 212000 | 2021-05-03 | 2021-10-03 | Plan | 24/03/2021 | 26/3/2021 | 31/03/21 | 212000
| Actual |  |  |  |  | Actual | [7 empty] | Actual | [6 empty] | Actual